## Translation
TRANSLATION

Section	Status	Papers	Coms
Precontent
Intro
Intro I
Intro 1
1.1	OK
1.2		Medium ebook
1.3		Medium ebook
CL 1
Intro 2
2.1	in progress
2.2			ECTQG17
2.3
CL 2
Intro 3
3.1
3.2		transportationEquilibrium
3.3	OK	Geodivercity-epistemo
Intro 3
CL I	OK
Intro II	in progress
Intro 4
4.1			RGS16
4.2		CausalityRegimes	ECTQG17
4.3		InteractionGibrat	CCS16
Cl 4
Intro 5
5.1		morphogenesis
5.2		density
5.3		correlatedSyntheticData
CL 5
CL II
Intro III
Intro 6
6.1	in prgress	Geodivercity-simpopnet
6.2	OK	citiesNetworks	Medium conf
CL 6
Intro 7
7.1	OK		CCS17
7.2	OK	urbanMorphology	CCS17
7.3	in progress	lutecia	ECTQG15
CL 7
CL III
Intro 8
8.1
8.2	OK		Medium seminar
8.3		KnowledgeFramework
CL 8
Conclusion
A.1
A.2
A.3
A.4
A.5
A.6
A.7
A.8
A.9
A.10
A.11
A.12
B.1
B.2
B.3
B.4		RobDiscrepency
B.5
B.6		Cybergeo
C.1
C.2
C.3
C.4		CybergeoNetworks
C.5
C.6
C.7
D.1
D.2
D.3
D.4
E.1
E.2
E.3
F.1
F.2

## Organisation
	Task	ETA 16/11	ETA 01/12	ETA 18/12	ETA 03/01	ETA 14/01	ETA 21/01	ETA 28/01	ETA 04/02
Introduction	revisions	4	4	4	0	0	0	0	0
Chapitre 1	revisions	16	8	8	0	0	0	0	4
	synthese processus	8	4	4	0	0	0	0	0
Chapitre 2	Reecriture 2.1	4	8	0	0	0	0	0	0
	Revisions 2.2 et 2.3	4	4	0	0	0	0	0	0
	synthese	4	4	0	0	0	0	0	0
Chapitre 3	Finitions 3.1	8	4	0	0	0	0	0	0
	revisions	8	4	0	0	0	0	0	4
Transition I-II	review coevol	8	4	2	0	0	0	0	0
Chapitre 4	Narrative 4.1	4	4	4	4	4	0	0	0
	Simplification figures	4	0	0	0	0	0	0	0
	revisions	20	20	20	16	16	0	0	4
Chapitre 5	Simplification figures	4	0	0	0	0	0	0	0
	revisions	16	16	16	8	8	0	0	4
Transition II-III	schema position modeles	4	4	4	4	4	4	0	2
Chapitre 6	Simplification figures	8	2	2	2	2	0	0	0
	Narrative/literature emp	8	4	4	4	4	4	2	0
	revisions	8	4	4	8	8	4	2	8
Chapitre 7	Finitions 7.1 et 7.2	32	32	32	32	8	0	0	0
	Traduction/adaptation 7.3	24	24	24	20	4	0	0	0
	revisions	0	0	0	0	0	0	0	8
Transition III-IV	synthese	8	4	4	4	4	4	1	0
Chapitre 8	narrative	2	2	2	2	2	2	0	0
Chapitre 9	reprise en perspective	8	4	4	4	4	4	4	0
	revisions	8	8	8	8	8	8	8	0
Conclusion	ecriture	16	16	16	16	16	16	16	0
Annexes	forme Annexe A	8	8	8	8	8	16	4	0
	forme Annexe B	8	4	4	4	2	2	2	0
	Paper Cybergeo : fin / trad		24	0	0	0	0	0	0
	forme Annexe C	8	4	4	8	4	4	4	0
	Paper CybNW : fin / trad		16	2	0	0	0	0	0
	Data description	8	8	8	8	4	2	2	0
	Software architecture	8	8	8	8	4	4	4	0
	Reflexivity	16	24	16	16	16	16	2	0

	Total	294	284	212	184	130	90	51	34
	Available (days)	50	71	59	43	34	27	21	13
	Available (8h days)	400	568	472	344	272	216	168	104
		1.36054421768707	2	2.22641509433962	1.8695652173913	2.09230769230769	2.4	3.29411764705882	3.05882352941176

## WorkingNotes
Title
Definitions

TODO
cheatsheet on multi-level modeling
cheatsheet on CI/distrib of pearson product moment

## WorkingPapers
Title	Project	Thematic	Keywords	Abstract
A Theoretical Framework for the Study of Socio-Technical Systems

Game-theory Based Behavioral Rules for Governing Agents in a Hybrid Land-Use Transportation Model
French High-Speed Network : Pragmatized State Top-Down Transportation Planning
Sensibility of Urban Scaling Exponents to City Definition
Reflexions on Context and Scales of Models
We are the frontier
A Unified Framework for Stochastic Models of Urban Growth
Using Synthetic Data to Control on Meta-Parameters for a Model of Simulation
A Structured Documentation Generator for NetLogo Models
Aggregating Multiple Source NetLogo Models
Reproducibility in Practice : Loosing your Balance on the Shoulder of Giants

## Papers
Title
Models Coupling Urban Growth and Transportation Network Growth : An Algorithmic Systematic Approach