## Experiments
Project	Model	Experiment	Notes	Runs	Environment	Status	Ready	Launched	Finished	File
MacroCoEvol	SimpopNet	Phase diagrams / Spatial Sensitivity	Behavior accross parameter space / Variation of phase diagrams as a function of meta-parameters	1.2e6	grid	finished	10/08/2017 ; packed and wrapped 22/08	22/09/2017	26/09/2017
	MacroCoEvol Abstract	Exploration	Synthetic exploration of abstract model		grid	finished	08/11/17	28/09/2017	29/09/2017
		Benchmark IntGib	Calibrate IntGib with fixed real distance matrices	nsga (100)	local	on hold	08/11/17	-	-
		Calibration Real	Bi or tri-objective moving window calibration	nsga (100)	local	finished	08/11/17	17/08/2017 ; cut 18/08 ; relaunched 29/09	01/10/17
	MacroCoEvol	Calibration Network shape	Test different network heurisitics			on hold		-	-
MesoCoEvol	MesoCoEvol Static Dens	Explo/Calib current real densities	Brute force exploration of nw heuristics, given density configs with simple initial network, to find both feasible space and distance to real network. Stopping condition on actual network length. Requires real nw and density config.	500000	grid	finished	08/18/17	08/18/17	08/21/17
	MesoCoEvol	Causality Regimes	Synthetic exploration, determination of causality regimes			finished		11/09/17	14/09/2017
		Calibration Real	Initialisation on real historical data synthetic data (same experiment as causality regimes); try to calibrate at first (indicators) and second order (correlations) for final real configs		grid	finished		11/09/2017 : synthetic setup	14/09/2017
Governance	Lutecia	Governance validation	stylized shape, average network			todo
		Fixed LU	Fixed LU, try to reproduce current network			todo
		Full	Full model, project medium term			todo
Space Matters	Schelling Netlogo	Fixed grids phase diagrams	45 JR grids, 100 repetitions, around 1000 parameter points	4.5e6	grid	finished	08/10/17	10/08/2017 ; failed 11/08;relaunched 22/08 packets	26/08/2017
		Random grid phase diagrams	idem sugarscape			on hold
		Exploration	Varying conjointly parameters and meta-parameters			on hold
Migration Dynamics	Mingong	Policies	Explore policies impact			on hold